## Sheet1
| Test case ID | Current Date | Expected Date | Role | Test Case Title | Issue Type | Test Scenario | Test Case Description | Test Step | Test Data | Screenshot Attechments | Expected Result | Acutal Result | log Type | Status | QA Comments | Priority | Sevearity | QA status | Dev Status | Dev Comments
1 | TC 01 | 20/09/2025 |  | User | Home page | UI | whether Website is Opening in all the browsers? | Need to check the browser in following browsers - (1) Chrome (2)Safari (3) Firefox (4) Edge | User has launched URL https://caregharper.com/ pasted on google chrome browser and Entered, Screen Opened with Home page | URL: https://caregharper.com/ | https://prnt.sc/LOzwgrswos38 https://prnt.sc/0yRDYQslhrPZ https://prnt.sc/0ohWO3EJPXvU | User should be open Website in : (1) chrome (2) Firefox (3) Safari (4) Edge | As Expected | Done | Pass |  | Low | Low | Verified
2 | TC02 | 20/09/2025 |  | User | Home page | Functional | Verify care support button functionality | When the User is clicks on Care support it gives a 404 error not found | User go to Home page -> click on care support button | N/A | https://prnt.sc/5joD-FfGE6W- https://prnt.sc/KPVjUyXUnlG1 | User will login to the website and then click on the care support button | Wnen user click on care support button errer is coming | Bug | Fail |  | High | High | Reopen
3 | TC03 | 20/09/2025 |  | User | Home page | UI | Photos are overlapping each other | When the user login to the website and click on the about button user should be able to see the UI, photo and all element displayed properly | User go to home page -> click About button | N/A | Lightshot screenshot | user should be able to see the UI and photo all element displayed properly and photo should not be overlapping | Photo is overlapping | Bug | Fail |  | Low | High | Reopen
4 | TC04 | 20/09/2025 |  | User | Home page | UI | Extra image is showing on top home page | When the user login to the website and user should be able to see the UI, photo and all element displayed properly | User has launched URL: https://caregharper.com/ pasted on google chrome browser and Entered, Screen Opened with Home page | N/A | https://prnt.sc/GvXT5w87uiuE | UI, photo and all element displayed properly | Extra image and line is visible in the home page | Bug | Fail |  | High | Mid | Reopen
5 | TC05 | 20/09/2025 |  | User | Home page | Functional | Verify Elderly care button functionality | When the User is clicking on Elderly Care button image but An Elderly Care details is not show details and give 404 error not found | User has launched URL: https://caregharper.com/ pasted on google chrome browser and Entered, Screen Opened with Home page | N/A | https://prnt.sc/RqSBu3cYKRRC | The elderly care button should be work and open properly and text or image show properly | The elderly care button is not showing image and text properly | Bug | Not Executed |  | Mid | High | Reopen
6 | TC06 | 20/09/2025 |  | User | Home page | UI | Verify Elderly care button image | when the user is opening website after that scroll page and an elderly care button should be show photo of elder | Home page -> Elderly care button | N/A | https://prnt.sc/tpPZ0dK4j8s9 ,https://prnt.sc/i4rEJfBGgF8Q | Verify the elderly care buttton should be show properly the elder photo | the elderly care button is not showing image properly | Bug | Fail | In elderly care buttton can we replace the women photo with add an elder photo | Mid | High | Reopen
7 | TC07 | 20/09/2025 |  | User | Home page | Functional | Verify Post-Surgery Care button functionality | when User is clicking on Post-Surgery Care button but Post-Surgery Care details is not showing text or image and give 404 error not found | Home page -> Post-Surgery care button | N/A | https://prnt.sc/wepUS26L_QJC , https://prnt.sc/-wwb69v_uU3F | The Post-Surgery care button should be work and open properly and text or image show properly | The Post-Surgery care button is not showing image and text properly | Bug | Not Executed |  | Low | High | Reopen
11 | TC11 | 20/09/2025 |  | User | Home page | Functional | Verify Child care button | When user is clicking on child Care button but Child Care details is not showing text or image and give 404 error not found | Home page -> Child Care button | N/A | https://prnt.sc/wJPW9peUKwga , https://prnt.sc/Yie7j5XeOY6l | The Child care button should be work and open properly and text or image show properly | The Child care button is not showing iamge and text properly | Bug | Not Executed |  | Mid | High | Reopen
12 | TC12 | 20/09/2025 |  | User | Home page | Functional | Verify that child care image | when the user is opening website after that scroll page and child care button should be show photo of child | Home page -> Child Care button | N/A | https://prnt.sc/zMEaum_nUdQC | child care button should be show photo of child | the child care button is not showing image properly | Bug | Fail |  | Mid | High | Reopen
14 | TC14 | 20/09/2025 |  | User | Home page | UI | Verify that Disability Care image | When user is opening website and scroll down side page and Disability Care image is not showing image properly | Home page -> Disability Care button | N/A | https://prnt.sc/QVQOWflDt80K | Disability care button should be show image properly | Disability care button is not showing image proper image is mismach | Bug | Fail | In Disablitiy care buttton can we replace the doctor or women photo with add an elder photo | Mid | Mid | Reopen
15 | TC15 | 20/09/2025 |  | User | Home page | Functional | Verify that Disability Care button | When User is clicking on Disability Care image but Disability Care details is not showing text or image and give 404 error not found | Home page -> Disability Care button | N/A | https://prnt.sc/f2XXQOCo0LlU , https://prnt.sc/d6HB-AaPcK2Y | Disability care button should be open and show text or image | Disability care button is not opening and showing text or image and show error | Bug | Not Executed |  | Low | High | Reopen
16 | TC16 | 20/09/2025 |  | User | Home page | Functional | Verify that Disability Care button | When user is opening website and click Disability Care button but details is not showing and give error 404 not found | Home page -> Disability Care button | N/A | https://prnt.sc/lp3OP68SjF5B , https://prnt.sc/QjMbvub1JybX | Disability care button should be open and work proper | Disability care button(Book Now) is not opening and working proper | Bug | Fail |  | Mid | High | Reopen
17 | TC17 | 20/09/2025 |  | User | Home page | Functional | Verify that Short-Term Nursing button | When User is opening website and click on Short-Term Nursing image but Short-Term Nursing details is not showing and give 404 error not found | Home page -> Short-Term Nursing button | N/A | https://prnt.sc/PumGnsmumIPM , https://prnt.sc/45kR4a7D37ir | Short-Term Nursing button should be open or show text or image and button work properly | Short-Term Nursing button is not opening or showing text or image and is not working button proper | Bug | Not Executed |  | Low | High | Reopen
18 | TC18 | 20/09/2025 |  | User | Home page | Functional | Verify that Short-Term Nursing button(Book Now) | When User clicks Short-Term Nursing button and button is clicked propar but details are not displayed and an error is show 404 not found | Home page -> Short-Term Nursing button | N/A | https://prnt.sc/OYswSrnsa-eB , https://prnt.sc/Lq0iBNwoiTT2 | Short-Term Nursing button should be open and button work proper | Short-Term Nursing button is not opening and is not woring button properly | Bug | Not Executed |  | Low | High | Reopen
19 | TC19 | 20/09/2025 |  | User | Home page | Functional | Verify that Long-Term Attendant button function | When User is clicks on Long-Term Attendant image button but all details is not show and give 404 error not found | Home page -> Long-Term Attendant button | N/A | https://prnt.sc/ti2T59WjYcPr , https://prnt.sc/xRqSSyKFO7BI | Long-Term Attendant button should be show and all details show proper | Long-Term Attendant image is not showing but Long-Term Attendant is not all details show proper | Bug | Fail |  | Mid | High | Reopen
20 | TC20 | 20/09/2025 |  | User | Home page | Functional | Verify that Long-Term Attendant button(Book Now) | When user clicks Long-Term Attendant button is not clickable and details is not show | Home page -> Long-Term Attendant button | N/A | https://prnt.sc/T7U8m_oNgerT , https://prnt.sc/o9hRfuqaI9FU | Long-Term Attendant button is working proper | Long-Term Attendant button is not working proper | Bug | Fail |  | Mid | High | Reopen
21 | TC21 | 20/09/2025 |  | User | Home page | UI | Screen Alignment form home | Verify that Screen Alignment is not right because is cutting off screen | User has launched URL: https://caregharper.com/ pasted on google chrome browser and Entered, Screen Opened with Home page | N/A | https://prnt.sc/oUXVhbmeJjHQ | Screen Alignment should be look very good and the alignment should not be cut off screen | Screen Alignment is not right because cutting off screen | Bug | Fail |  | Mid | High | Reopen
22 | TC22 | 20/09/2025 |  | User | Home page | UI | Photo is missing from testimonials | When use opened the website then scrolled dwon side page and saw that in the testimonials sectioin but a girl photo was palaced instead of a boy here | User has launched URL: https://caregharper.com/ pasted on google chrome browser and Entered, Screen Opened with Home page-> scrolled down, clicked testimonials | N/A | https://prnt.sc/WHp17qB0qSZO | User saw that in the testimonials sectioin photo was should be palaced of a boy | User saw that in the testimonials sectioin but a girl photo palaced instead of a boy here | Bug | Fail | Change testimonials photo from girl to boy | High | High | Reopen
23 | TC23 | 20/09/2025 |  | User | Home page | UI | Testimonials comments | When user comes to the website and reaches the testimonials, he starts reading commends. But comments stay only for a short time, so thet user cannot read them fully they moves forward quickly. if he wants to read something, he should be able to click on it and read it for longer time. | User has launched URL: https://caregharper.com/ pasted on google chrome browser and Entered, Screen Opened with Home page-> scrolled down, clicked testimonials | N/A | https://prnt.sc/-p-nXx4FAfCu | User wants to read should be able to commend click on it and read it for longer time. | User is not reading able to comment because slide is running fast and is not reading it for longer time. | Bug | Fail |  | Low | Mid | Reopen
24 | TC24 | 20/09/2025 |  | User | Home page | UI | Our solutions page | Verify that user saw our solutions image page alignment is not matching and alignment up and down | User has launched URL: https://caregharper.com/ pasted on google chrome browser and Entered, Screen Opened with Home page-> scrolled down, clicked Our Solutions page. | N/A | https://prnt.sc/J5m68pr0W_kG | Our Solutions page the alignment should not be damage and should flow up and down. | Our solutions page of the alignment is broken and is running up and down | Bug | Fail |  | Mid | High | Reopen
25 | TC25 | 20/09/2025 |  | User | Home page | UI | Our solutions page | Verify our soulution image given on the right side and left side is getting broken from both sides | User has launched URL: https://caregharper.com/ pasted on google chrome browser and Entered, Screen Opened with Home page-> scrolled down, clicked Our Solutions page. | N/A | https://prnt.sc/yBDpLqFR-qOu | Our Solutions page the image should not be broken and should be flow up and down. | Our solutions page image is of broken | Bug | Fail |  | Mid | High | Reopen
26 | TC26 | 20/09/2025 |  | User | Home page | Functional | Home Medical Checkup | When user is clicking on the Home Medical Checkup button but is not showing details, text or image and that it give 404 error not found | User has launched URL: https://caregharper.com pasted on google chrome browser and Entered, Screen Opened with Home page-> scrolled down, clicked Home medical checkup. | N/A | https://prnt.sc/YB9qNxIktRyd , https://prnt.sc/CEJNfdNKyxIP | user should be click on the Home Medical Checkup button and should be show all details,text and image | the Home Medical Checkup button but details is not showing all details, text or image | Bug | Fail |  | Mid | High | Reopen
27 | TC27 | 20/09/2025 |  | User | Home page | Functional | Personalized care | When user is clicking on Personalized care button but is not showing details, text or image and that it give 404 error not found | User has launched URL: https://caregharper.com pasted on google chrome browser and Entered, Screen Opened with Home page-> scrolled down, clicked Personalized care. | N/A | https://prnt.sc/1LUemVVJAlbn , https://prnt.sc/MP6i_E49S2kk | user should be click on the Personalized care button and should be show all details,text and image | the Personalized care button but details is not showing all details, text or image | Bug | Fail |  | Mid | High | Reopen
28 | TC28 | 20/09/2025 |  | User | Home page | Functional | Senior citizen care | When user is clicking on Senior citizen care button but is not showing details, text or image and that it give 404 error not found | User has launched URL: https://caregharper.com/ pasted on google chrome browser and Entered, Screen Opened with Home page-> scrolled down, clicked Senior citizen care. | N/A | https://prnt.sc/-bXblrVf2Oio , https://prnt.sc/JiZhg4W73lvf | user should be click on the Senior citizen care button and should be show all details,text and image | the Senior citizen care button but details is not showing all details, text or image | Bug | Fail |  | Mid | High | Reopen
29 | TC29 | 20/09/2025 |  | User | Home page | Functional | Residential care | When user is clicking on Residential care button but is not showing details, text or image and that it give 404 error not found | User has launched URL: https://caregharper.com pasted on google chrome browser and Entered, Screen Opened with Home page-> scrolled down, clicked Residential care. | N/A | https://prnt.sc/ZY6wlulDPeW1 , https://prnt.sc/3rWeI3eRXirF | user should be click on the Residential care button and should be show all details,text and image | the Residential care button but details is not showing all details, text or image | Bug | Fail |  | Mid | High | Reopen
30 | TC30 | 20/09/2025 |  | User | Home page | Functional | Discover more Button | When user clicks Discover more button and user go inside is spelling mistakes. | User has launched URL: https://caregharper.com pasted on google chrome browser and Entered, Screen Opened with Home page-> scrolled down, clicked Discover more button, Need any help. | N/A | https://prnt.sc/jX1rfPssXBha | Discover more button click and user go inside is not spelling mistakes. | Discover more button click and user go inside is spelling mistakes. | Bug | Fail |  | Mid | High | Reopen
31 | TC31 | 20/09/2025 |  | User | Home page | Functional | Discover more Button | user clicks discover more button and enter inside page but send massage is not working | User has launched URL: https://caregharper.com pasted on google chrome browser and Entered, Screen Opened with Home page-> scrolled down, clicked Discover more button, Send us email. | N/A | https://prnt.sc/1zsZoSd6E78N | send massage should be work and clickable | Send massage is not work | Bug | Fail |  | Mid | High | Reopen
32 | TC32 | 20/09/2025 |  | User | Home page | Functional | Discover more Button | user clicks discover more button and after entering name, Subject and Phone field the requirement for the all field should appear below it. | User has launched URL: https://caregharper.com pasted on google chrome browser and Entered, Screen Opened with Home page-> scrolled down, clicked Discover more button, Send us email | N/A | https://prnt.sc/qjWmL4MQTVaQ | user enter in the field incorrectly anme,phone and subject massage show "This field is required" appear below the field. | "This field is required" is not showing appear below the field. | Bug | Fail | all field should be appear below the field "this field is required" | Mid | High | Reopen
33 | TC33 | 20/09/2025 |  | User | Home page | Functional | Discover more Button | if user in the field enter wrong name should not click submit button | User has launched URL: https://caregharper.com pasted on google chrome browser and Entered, Screen Opened with Home page-> scrolled down, clicked Discover more button, Send us email | user enters incorrect Name: gkjhkjh | https://prnt.sc/JcGps7vmqkYs | user must enter the correct name in the field then it will be submit button and go to the next page. | user enters the incorrect name in the field and enter submit button wrong massage is not giving and going to the next page. | Bug | Fail | Enter the correct name then enter submit button | Mid | High | Reopen
34 | TC34 | 20/09/2025 |  | User | Home page | Functional | Discover more Button | if user in the field enters wrong Subject should not click submit button | User has launched URL: https://caregharper.com pasted on google chrome browser and Entered, Screen Opened with Home page-> scrolled down, clicked Discover more button, Send us email | user enters incorrect Subjcet: gfdgdgfgrf3@#4 | https://prnt.sc/bAu77UT5DvzF | If user must enter the correct Subject in the field then it will be submit and go to the next page. | if user enters the incorrect Subject in the field and enter submit button wrong massage is not giving and going to the next page. | Bug | Fail | Enter the correct Subject then enter submit button | Mid | High | Reopen
35 | TC35 | 20/09/2025 |  | User | Home page | Functional | Discover more Button | if user in the field enters wrong should not click submit button | User has launched URL: https://caregharper.com pasted on google chrome browser and Entered, Screen Opened with Home page-> scrolled down, clicked Discover more button, Send us email | user enters incorrect Number : 1234764580 | https://prnt.sc/jZu4TcFC6ao- | user enter the correct Number in the field then it will be submit button and go to the next page | if user enters the incorrect Nuber in the field and enter submit button wrong massage is not giving and going to the next page. | Bug | Fail | Enter the correct Number the enter submit button | Mid | High | Reopen
36 | TC36 | 20/09/2025 |  | User | Home page | Functional | Discover more Button | When user opens the website, if any function does not work he will click on the help button if needed but call button is not working and is giving an error massage. | User has launched URL: https://caregharper.com pasted on google chrome browser and Entered, Screen Opened with Home page-> scrolled down, clicked Discover more button, Need any help. | N/A | https://prnt.sc/ptcziY0pNGkT | If user has any problem then call button should be work | Call button is not working. | Bug | Fail |  | Mid | High | Reopen
37 | TC37 | 20/09/2025 |  | User | Home page | Functional | Discover more Button | When user opens the website, if any function does not work he will click on the help button if needed but Write email button is not working and is giving an error massage. | User has launched URL: https://caregharper.com pasted on google chrome browser and Entered, Screen Opened with Home page-> scrolled down, clicked Discover more button, Need any help. | N/A | https://prnt.sc/uwxVvgEPRNKb , https://prnt.sc/VyphgrMtuWH2 | If user has any problem then write email should be work | Write email button is not working. | Bug | Fail |  | Mid | High | Reopen
38 | TC38 | 20/09/2025 |  | User | Home page | Functional | Discover more Button | When user opens the website, if any function does not work he will click on the help button if needed but visit anytime button is not working . | User has launched URL: https://caregharper.com pasted on google chrome browser and Entered, Screen Opened with Home page-> scrolled down, clicked Discover more button, Need any help. | N/A | https://prnt.sc/i213Q7BP76ig | If user has any problem then visit anytime should be work | Visit anytime button is not working. | Bug | Fail |  | Mid | High | Reopen